## Sheet1
Sprint 1
Dev Features | Estimate time (hr) | Author | Actual time | Reason
Display the number of times an author appears first/last on a paper | 5 | Martin/Heng | 5
Make all tables sortable | 10 | Thomas/Martin | 12 | requirement issue
Testing Features
Fix original project issue | 3 | Ghada | 3
Add UT cases for project | 4 | Heng | 4 |  | estimate time | actual time
Add UT cases for new feature | 3 | Jing | 3 |  | 0 | 0
total | 25 |  | 27 |  | 25 | 27
[5 empty] | 38 | 42
Sprint 2 |  |  |  |  | 60 | 66
Dev Features | Estimate time (hr) | Author | Actual time | Reason
Search Features | 5 | Thomas | 7 | TDD issue
Sorting enhancement | 1 | Martin | 1
Sole Author feature | 1 | Martin | 1
Testing Features
Search Features | 2 | Heng | 2
Sorting enhancement (manually) | 2 | Jing | 2
Sole Author feature | 2 | Ghada | 2
total | 13 |  | 15
Sprint 3
Dev Features | Estimate time (hr) | Author | Actual time | Reason
Sorting second criterion | 5 | Martin | 8 | Commnication with client, implementaton details
Publication by author | 5 | Thomas | 5
Click feature | 3 | Thomas | 3
Search enhancement | 3 | Martin | 3
Testing Features
Publication by author | 2 | Heng | 2
Click feature | 2 | Jing/Ghada | 2
view improvement | 2 | Martin | 2
total | 22 |  | 24
Sprint 4
Dev Features | Estimate time (hr) | Author | Actual time | Reason
UI enhancement | 8 | Martin | 12 | UX need to be considered
d3.js related | 8 | Thomas | 8
feature 1 | 3 | Ghada/Heng/Jing | 5 | feature 4 is related with feature 1, more stuff need to be considred
Testing Features
UI enhancement | 2 | Martin | 2
d3.js related | 2 | Thomas | 2
feature 1 | 2 | Ghada/Heng/Jing | 5 | More test required
Total | 25 |  | 34